UNIVERSITY EXAMINATIONS

EXAMINATION FOR MAY/AUGUST 2022/2023 DIPLOMA IN COMPUTER SCIENCE/DIPLOMA IN INFORMATION TECHNOLOGY/ DIPLOMA IN BUSINESS INFORMATION TECHNOLOGY

COURSE CODE: RIT024 COURSE UNIT: PROJECT MANAGEMENT

DATE: 4TH AUGUST 2023	TIME: 2 HOURS

GENERAL INSTRUCTIONS:

Students are NOT permitted to write on the examination paper during examination time.

This is a closed book examination. Text book/Reference books/notes are not permitted.

SPECIAL INSTRUCTIONS:

This examination paper consists Questions in Section A followed by section B.

Answer Question 1 and any Other Two questions.

QUESTIONS in ALL Sections should be answered in answer booklet(s).

# PLEASE start the answer to EACH question on a NEW PAGE.

# Keep your phone(s) switched off at the front of the examination room.

# Keep ALL bags and caps at the front of the examination room and DO NOT refer to ANY unauthorized material before or during the course of the examination.

# ALWAYS show your working.

# Marks indicated in parenthesis i.e. ( ) will be awarded for clear and logical answers.

# Write your REGISTRATION No. clearly on the answer booklet(s).

# For the Questions, write the number of the question on the answer booklet(s) in the order you answered them.

- DO NOT use your PHONE as a CALCULATOR.

- YOU are ONLY ALLOWED to leave the exam room 30minutes to the end of the Exam.

- DO NOT write on the QUESTION PAPER. Use the back of your BOOKLET for any calculations or rough work.

SECTION A (COMPULSORY)

QUESTION ONE (30 MARKS)

- Give a detailed explanation of how you understand the following terms as used in Project Management.

    - Project

    - Project manager

    - Project Charter						(6 marks)

- In any project schedules are a key aspect of project management. A software development project had the following activities.

| Activity | Predecessor | Duration in Weeks |
| --- | --- | --- |
| A | - | 5 |
| B | - | 7 |
| C | A | 6 |
| D | B | 5 |
| E | B | 4 |
| F | D,E | 8 |
| G | C,F | 8 |
| H | D | 6 |
| I | G,H | 3 |

Required:

- Draw the necessary diagram and calculate the critical path for the project.      (10 marks)

- Define project management and explain its importance in achieving project success.	                                                                               										    (6 marks)

- Discuss the major elements of project risk management and strategies to mitigate project risks.										    (4 marks)

QUESTION TWO (20 MARKS)

- What are the different types of project organizational structures? Discuss their advantages and disadvantages. 								    (6 marks)

- Explain the key steps involved in project initiation and the importance of conducting a feasibility study.						                         (6 marks)

- What are the qualities of good software?					 (5 marks)

- Being assigned as a project manager you noticed during project execution that conflict arises in the team at both technical and inter-personal levels. What is an appropriate way of handling conflicts? 							 	 (3 marks)

QUESTION THREE (20 MARKS)

- Explain five characteristics of a project					   (5 marks)

- Give an elaborate four problems that particularly affect students’ projects.     (8 marks)

- Discuss the concept of project cost management and the key processes involved

(7 marks)

QUESTION FOUR (20 MARKS)

- Explain the importance of effective communication and stakeholder management in project management.                            					    (4 marks)

- Using the diagram discuss three organizational structural 			    (6 marks)

- Discuss the advantages and disadvantages of using organizational structural. (5 marks)

- Discuss the role of a project manager in managing project resources, including human resources and procurement.							   (5 marks)

QUESTION FIVE (20 MARKS)

- Discuss the responsibilities of project manager.	                        	   (5 marks)

- What are rge different types of project constraints?									 			                                                   (5 marks)

- Describe five positive and five negative effect of conflict in project		   (10 marks)