UNIVERSITY EXAMINATIONS

EXAMINATION FOR SEPTEMBER/DECEMBER 2024/2025 DIPLOMA IN COMPUTER SCIENCE/DIPLOMA IN INFORMATION TECHNOLOGY/DIPLOMA IN BUSINESS INFORMATION TECHNOLOGY/DIPLOMA IN CYBER SECURITY

COURSE CODE RIT 024 : COURSE UNIT ICT PROJECT MANAGEMENT

DATE: __DECEMBER   2024	TIME: 2 HOURS

GENERAL INSTRUCTIONS:

Students are NOT permitted to write on the examination question paper during exam time.

This is a closed book examination. Text book/Reference books/notes are not permitted.

SPECIAL INSTRUCTIONS:

This examination paper consists Questions in Section A followed by section B.

Answer Question 1 and any Other Two questions.

QUESTIONS in ALL Sections should be answered in answer booklet(s).

# PLEASE start the answer to EACH question on a NEW PAGE.

# Keep your phone(s) switched off at the front of the examination room.

# Keep ALL bags and caps at the front of the examination room and DO NOT refer to ANY unauthorized material during the course of the examination.

# ALWAYS show your working.

# Marks indicated in parenthesis i.e. ( ) will be awarded for clear and logical answers.

# Write your REGISTRATION No. clearly on the answer booklet(s).

# For the Questions, write the number of the question on the answer booklet cover page in the order you answered them.

- DO NOT use your PHONE as a CALCULATOR.

- YOU are ONLY ALLOWED to leave the exam room 1hour to the end of the Exam.

- DO NOT write on the QUESTION PAPER. Use the back of your BOOKLET for any calculations or rough work.

### Instructions:  Answer Question ONE (Compulsory) and any other TWO questions.

### QUESTION ONE (30 Marks)

TechSolve Inc., a renowned software solutions provider, has undertaken a large-scale project to design and implement an advanced IT system for a multinational corporation. The aim of the project is to streamline the client's business processes by integrating functions such as data management, workflow automation, telecommunications, hardware setup, system testing, training, and final deployment. The project manager, David, is responsible for ensuring the project adheres to strict timelines, stays within budget, and fulfills the client's extensive requirements. David must navigate the challenges posed by the triple constraints of time, cost, and scope, while effectively managing team resources and mitigating project risks.

a) Define Process Management.							[1 Mark]

b) Explain ICT Project Management and its key components			.[1 Mark]

c) What is a Project Charter, and what role does it play in project management?
											[1 Mark]

d) Identify and explain the triple constraints in project management and their impact on a project's success.									 [3 Marks]

e) Outline the stages involved in the project planning process and briefly explain each.
											[4 Marks]

f) Discuss four common reasons why IT projects fail and their consequences	.[4 Marks]

g) Explain the four processes of managing human resources in a project		. [4 Marks]

h) List and describe four risk response strategies in project management.		[4 Marks]

i) Given the table below, assuming the project team works a standard 5-day week and tasks start as early as possible:

| Task | Description | Duration (Working Days) | Predecessor(s) |
| --- | --- | --- | --- |
| A | Requirements Analysis | 5 |  |
| B | Systems Design | 15 | A |
| C | Programming | 25 | B |
| D | Telecoms | 15 | B |
| E | Hardware Installation | 30 | B |
| F | Integration | 10 | C, D |
| G | System Testing | 10 | E, F |
| H | Training/Support | 5 | G |
| I | Handover and Go-Live | 5 | H |

i. Identify the critical path of the project.						[3 Marks]

ii. Determine the total project duration and convert it to weeks.			[3 Marks]

iii. List the non-critical tasks and calculate their float				[1 Mark]

### QUESTION TWO (15 Marks)

a) Define portfolio direction and explain its significance in project governance	.[2 Marks]

b) Discuss three functions of project sponsorship in the context of governance	.[3 Marks]

c) Explain how project management effectiveness and efficiency are achieved and measured.
											[2 Marks]

d) Describe four key benefits of disclosure and reporting in project governance	.[5 Marks]

e) Define continuous improvement in project management.				[3 Mark]

### QUESTION THREE (15 Marks)

a) Discuss the characteristics of cost components and compare two approaches to estimating project costs. Why is good cost planning crucial in project management?		 [4 Marks]

b) Explain the importance of SMART milestones in project management. Define SMART and describe how it applies to milestone setting in large projects. 			[3 Marks]

c) Identify four distinct factors an ICT Project Manager should consider when preparing a project communications plan.									[8 Marks]

### QUESTION FOUR (20 Marks)

a) Describe six project management knowledge areas and their significance for project managers.										[6 Marks]

b) Identify and explain four types of risks encountered during project management.
											[4 Marks]

c) Describe four conflict resolution modes that a project manager can utilize when managing team conflicts.										[5 Marks]

### QUESTION FIVE (15 Marks)

a) Differentiate between the Project Evaluation and Review Technique (PERT) and the Critical Path Method (CPM). Highlight their unique features and applications. 		[4 Marks]

b) Describe the phases of the project life cycle, giving an example of activities and deliverables for each phase. 								[3 Marks]

d) Discuss five strategies or techniques a Project Manager might use to optimize resource allocation in a project. 							[8 Marks]